## Slide 1: 2021: Bring Talent Management to the next level
March
Feb
Jan
April
May
June
July
Aug
Sept
Oct
Nov
Dec
Development Plan
Follow-up
Talent Review
Follow-up & update
iDevelop
Development Plan
Work on Action Plans
Work on Action Plans
Talent Review
Assess Potential
April 1st to 26th
Country/Division Calibration
April 26th to June 11th
ELT
June 24th
April 1st to July 16th
Development plan:
Reach not only quantitative but qualitative results
Simplified development plan template
Focus on 70 and 20 parts of Ipsen learning model
Discussion guides, communication dedicated to managers/employees and workshop for managers/HR
Continuous Feedback
Feedback
Talent Review:
Assessment of all Ipsen employees
Ensure identification of early in career top talent/next generation leader
Optimize use of iPeople tool to get accurate talent data
Processes aligned in time to have simultaneously talent reviews & development plans nurturing one another with continuous feedback and respect of diversity and inclusion
Feedback culture:
Make Feedback a continuous initiative owned by all Ipsen employees
Educate and provide guidance to improve the Feedback culture at Ipsen (guides, eLearning, workshops)
Practice Feedback all along the year
April 1st to July 1st

## Slide 2: 2021 iDevelop (Development Plan & Talent Review) - Actions Timeline
Actions for BHRs, Site HRs and Talent Partners (please pencil dates in your calendar & start scheduling) |  |  | 
Actions | Development Plan | Talent Review | Dates
Attend meeting via Teams Ask questions | HR Training (presented by TM & HRIS) for BHRs, Site HRs, Talent Partners Session will be recorded, slide deck sent. |  | March 25th 13:30-15:00 CET
Materials ready for translation and deployment: Emails Managers Training slide deck | Mail Chimp ready for campaign launch Audience: all employees | Mail Chimp ready for campaign launch Audience: all HRs & managers with focus on all employee potential assessments | March 25th
Schedule and perform Managers training sessions | Focus on : Defining development needs & actions based on 70-20-10 learning model Talent data update Feedback culture | Focus on : Performing all GLT + all employees’ potential assessment by April 26th Identifying critical positions, defining succession plans | First week of April
Monitor |  | Completion of all GLT and all employees’ potential assessment | April (deadline April 26th )
Schedule Meeting with Manager |  | Support on GLT + employees’ potential assessments Identify and/or review critical positions Define succession plans | Before Talent Review meeting
Schedule Talent Review meeting |  | Step 1: Perform country/function talent review meeting (calib.) Step 2: Perform Division talent review meeting (calibration) | April 26th- June 11th
Monitor | Development plan completion rate Development plan quality (% of 70-20-10 actions, random check and adhoc actions for empty fields) |  | April 1st - July 16th
Start running reports regularly
Start running reports regularly